## Instructions
Mobile HR (HCM_50) — Device UAT Test Script
Flutter app • on-device testing • new work M495-M512 over the existing screens
How to use | Run the app on a phone or emulator. Do exactly what the Steps say, compare to the Expected Result, pick Pass / Fail / Blocked / Not Run. Note device model + OS in Tester Notes. Fill the Sign-off sheet.
App / backend | Flutter app in mobile/ (flutter run, or build an APK). Backend on the configured API base; Keycloak for login. Some features need device sensors (GPS, biometric, camera).
Delivered (new) | Attendance clock-in + GPS/geofence (M496/M497) + offline punch queue (M508) + corrections (M498); announcements (M499); policy acknowledgement (M500); HR service requests (M501); document upload (M502); profile edit (M503); employee directory (M504); notifications center (M505); settings + language (M506); offline read cache (M507); payslip re-auth + screenshot block (M509); team calendar (M510); leave enhancements + self-cancel (M511); bulk approvals (M512). Existing screens (login/home/leave/payslip/timesheet/training/goals/team) already shipped earlier.
Logins | Employee (self-service + confidentiality), Manager (team calendar, bulk approvals). Mark manager-only rows Blocked if you only have an employee login.
Result values | Pass / Fail (add a note) / Blocked / Not Run.
KEY RULES under test | Thin client: the app shows only what the backend returns for YOU. Payslip amounts require re-auth and are never cached in plaintext. Directory = public fields only. Team calendar hides leave type. Location capture shows a consent notice. Tokens live in secure storage. Any leak of salary/bank/another person's data = automatic Fail + report.

## Test Cases
Test ID | Feature Area | Login As | Test Steps (what to tap / do) | Expected Result | Result | Tester Notes
SET-01 | Setup | Any | Install the app on a device/emulator (flutter run or the built APK). Confirm the backend is reachable and Keycloak login works. Note the home screen tiles. | App launches, login via Keycloak succeeds, home shows tiles incl. new: Attendance, Announcements, Policies, HR Requests, Documents, Directory, plus a notification bell.
AUTH-01 | Auth / biometric | Employee | Log out, log back in. Then background+foreground the app and confirm biometric unlock (if enabled in Settings). | Keycloak OIDC login works; biometric (Face/fingerprint) unlocks a stored session; PIN/device-credential fallback works.
ATT-01 | Clock in/out (M496) | Employee | Attendance tile → grant location permission (consent notice shown) → Clock In. Then Clock Out. | Punch records; today-status card updates; punch history shows the entries; geofenceStatus (INSIDE/OUTSIDE/UNKNOWN) + flagged shown; location-recorded notice appeared.
ATT-02 | Geofence (M496/M497) | Employee | With a work location configured with GPS coords + radius, clock in from inside vs (simulate) outside the radius. | Inside → INSIDE, not flagged. Outside → OUTSIDE + flagged (still recorded, routed for review). If no geofence configured, punch allowed without geofence.
ATT-03 | Offline punch queue (M508) | Employee | Turn on airplane mode, Clock In (queues). See pending-sync count. Restore network, tap Sync now (or reopen the screen). | Offline punch queues with device timestamp; on reconnect it syncs to the server; no duplicate is created on re-sync (idempotent).
ATT-04 | Corrections (M498) | Employee | Attendance → Corrections → submit a missing-punch correction with a reason. | Correction submits to the backend and appears in the corrections list.
ANN-01 | Announcements (M499) | Employee | Announcements tile → open an announcement. | Active announcements list (date/audience); tapping shows full body.
POL-01 | Policy ack (M500) | Employee | Policies tile → open a published policy → Acknowledge. | Policy body shows; Acknowledge records a timestamp; the policy then shows as acknowledged.
HRR-01 | HR requests (M501) | Employee | HR Requests tile → submit a ticket (category + subject + description). View it in My Requests; add a comment. | Ticket submits with an SR-number/status; comments post and display.
DOC-01 | Document upload (M502) | Employee | Documents tile → pick a photo/file, choose a type, upload. | Upload shows progress and succeeds; the document appears in the list with its type.
PRO-01 | Profile edit (M503) | Employee | Profile → Edit Profile → change phone / emergency contact → submit. | Each changed field submits as a change request (pending approval); bank/salary are not editable; pending state shown.
DIR-01 | Directory (M504) | Employee | Directory tile → search a colleague → open their card → tap phone / email. | Search returns public fields only (name/dept/position/work email+phone); NO salary/bank/national-id/DOB/home address; tel:/mailto: launch.
NTF-01 | Notifications center (M505) | Employee | Tap the bell → view in-app notifications → mark read → tap one that deep-links. | Notifications list with unread badge; mark-read works; tapping navigates to the related screen where supported.
SET-02 | Settings (M506) | Employee | Settings → toggle language en↔az, toggle biometric, view app version/session. | Language toggle re-localizes date/time pickers; biometric toggle persists; version/session shown.
PAY-01 | Payslip security (M509) | Employee | Payslips tab → confirm a biometric/PIN re-auth is required before amounts show. Try to screenshot (Android). | Amounts hidden until re-auth (5-min validity); Android blocks the screenshot (FLAG_SECURE); iOS is best-effort (documented).
OFF-01 | Offline read cache (M507) | Employee | Load profile / leave balances / announcements / policies online, then go offline and reopen them. | Cached data shows with an 'offline / cached' banner; payslip amounts are NOT available offline (never cached).
TEAM-01 | Team calendar (M510) | Manager | As a manager, open the Team Calendar tile. | Team leave/BT/holidays render; entries show 'On Leave' — NOT the specific leave type. A non-manager doesn't see the tile / gets an empty state.
LV-01 | Leave enhancements (M511) | Employee | Leave → submit with half-day toggle + a replacement + an attachment. Then cancel a PENDING request. | Half-day/replacement/attachment all submit; a pending request can be cancelled by the employee (own only) and the balance restores.
APR-01 | Bulk approvals (M512) | Manager | Approvals → multi-select mode → select 2+ items → Approve selected (confirm). | Batch approve runs per item; per-item result summary shown; items you can't act on fail individually without blocking the rest.
SEC-01 | Confidentiality / IDOR | Employee | Try (via the app or by crafting API calls) to read another employee's payslip, wallet, directory-private fields, or documents. | All denied/absent: the app only shows what the API returns for YOU; payslip/self endpoints scope to the logged-in employee; directory exposes public fields only.
SEC-02 | No plaintext secrets | Tester/Dev | Inspect device storage / the offline cache after use. | Auth tokens are in secure storage (Keychain/Keystore), not plaintext; no salary/payslip/bank data in the shared-preferences cache; no secrets hardcoded in the app.

## Sign-off
Mobile HR UAT — Sign-off
Feature Area | Result | Tester | Date
Auth / biometric (AUTH)
Attendance + geofence + offline (ATT)
Announcements (ANN)
Policy ack (POL)
HR requests (HRR)
Document upload (DOC)
Profile edit (PRO)
Directory (DIR)
Notifications (NTF)
Settings/language (SET-02)
Payslip security (PAY)
Offline cache (OFF)
Team calendar (TEAM)
Leave enhancements (LV)
Bulk approvals (APR)
Confidentiality + secrets (SEC)
Overall decision (SHIP / DON'T SHIP):
Tester name:
Device + OS:
Date: