## Instructions
Performance Management — User Acceptance Test (UAT) Script
HCM_12 Performance Management • front-end (browser) testing • grows as each phase ships
How to use | Open the 'Test Cases' sheet. Do exactly what the Steps say (which tab, which button, what to type), compare to the Expected Result, and pick Pass / Fail / Blocked / Not Run in the Result column. Add anything unusual under Tester Notes. Fill the Sign-off sheet at the end.
Application URL | http://localhost:5180 — sign in first. Performance features are under the top-nav 'Performance' menu.
Delivered so far | Phase A (configuration foundation): rating scales with score bands (M388), review templates with weighted sections + cycle audience scoping (M389), KPI library + per-cycle assignments with automatic achievement/rating scoring (M390), OKR objectives + key results + check-ins with progress roll-up (M391).
Logins you will need | HR Admin (full performance admin), HR Specialist (read-only checks), Manager (team KPI/OKR), Employee (self-service scoping checks). If you only have an admin login, mark role-restriction rows Blocked with a note.
Result values | Pass = worked as expected. Fail = did not match (add a note). Blocked = could not run (missing login/data). Not Run = skipped.
Good to know | Rating-scale bands convert numeric scores to ratings during weighted scoring (Phase B). Templates fix which sections a review has and their weights (scoring sections must total 100). KPI ratings compute automatically: LINEAR = achievement ÷ 20 (100% → 5.0); THRESHOLD = bands ≥110→5 / ≥100→4 / ≥80→3 / ≥60→2 / else 1. OKR objective progress = weighted average of key-result progress.

## Test Cases
Test ID | Feature Area | Login As | Test Steps (what to click / type) | Expected Result | Result | Tester Notes
SET-01 | Setup | HR Admin | Sign in as HR Admin at http://localhost:5180. Open the top-nav 'Performance' menu. You should see (among others): Rating scales, Review templates, KPIs, OKRs, Review cycles, Goals. | The Performance menu shows the new entries: Rating scales, Review templates, KPIs, OKRs.
SCL-01 | Rating scales (M388) | HR Admin | Performance → Rating scales. | The seeded 'Default 5-point scale' (DEFAULT_5PT) is listed, marked Default + Active, with 5 values: 1 Unsatisfactory, 2 Needs Improvement, 3 Meets Expectations, 4 Exceeds Expectations, 5 Outstanding.
SCL-02 | Rating scales (M388) | HR Admin | Open the default scale (Edit) and look at each value's score band (min–max %). | Bands are ascending and non-overlapping: 0–39.99, 40–59.99, 60–74.99, 75–89.99, 90–100. (These drive the numeric-score → rating conversion in weighted scoring.)
SCL-03 | Rating scales (M388) | HR Admin | Click 'New scale…'. Code=SIMPLE_3PT, Name=Simple 3-point, Type=Numeric, add 3 values (1 Low / 2 OK / 3 High) with bands 0–49.99 / 50–79.99 / 80–100. Save. | The new scale appears in the list, Active, showing 3 values.
SCL-04 | Rating scales (M388) | HR Admin | Edit SIMPLE_3PT and set overlapping bands (e.g. value 2 = 40–80 while value 1 = 0–49.99). Save. | Rejected — score bands must be ascending and non-overlapping; an error is shown.
SCL-05 | Rating scales (M388) | HR Admin | Edit SIMPLE_3PT and tick 'Default scale'. Save. Reopen the list. | SIMPLE_3PT becomes Default and DEFAULT_5PT loses its Default tag (only one default at a time). Set DEFAULT_5PT back to default afterwards.
TPL-01 | Review templates (M389) | HR Admin | Performance → Review templates. | The seeded 'Default annual review' (DEFAULT_ANNUAL) template is listed with 8 sections; the scoring-weight total shows 100 (Goals 50 + KPIs 25 + Competencies 20 + Company Values 5; comment/development/final sections carry no weight).
TPL-02 | Review templates (M389) | HR Admin | Click 'New template…'. Code=SALES_ANNUAL, Name=Sales annual review. Add sections: Goals 40, KPIs 40, Competencies 20, plus Manager Comments (0). Watch the weight tag as you type. | The live scoring-weight tag turns from red to green exactly when the scoring weights total 100; Save succeeds.
TPL-03 | Review templates (M389) | HR Admin | Create another template whose scoring sections total 90 (e.g. Goals 50 + KPIs 40). Save. | Rejected — scoring-section weights must total exactly 100; an error is shown.
TPL-04 | Cycle scoping (M389) | HR Admin | Performance → Review cycles → New cycle (or edit an existing one). Note the new fields: Rating scale, Review template, and audience filters (legal entity / department / grade / employee type / min service months). | The cycle form offers the rating scale and template dropdowns (defaults pre-selected) and the audience-scoping fields; saving keeps them.
KPI-01 | KPIs (M390) | HR Admin | Performance → KPIs → Library tab → 'New KPI'. Code=SALES_TGT, Name=Quarterly sales target, Unit=AZN, Default target=50000, Frequency=Quarterly, Scoring=Linear, Source=Manual. Save. | The KPI appears in the library with the LINEAR tag.
KPI-02 | KPIs (M390) | HR Admin | Create a second KPI. Code=CSAT, Name=Customer satisfaction, Unit=%, Default target=90, Scoring=Threshold bands. Save. Then try creating a third KPI re-using code SALES_TGT. | CSAT saves with the THRESHOLD tag; the duplicate SALES_TGT is rejected (code must be unique).
KPI-03 | KPI assignment (M390) | HR Admin | KPIs → Assignments tab → pick a Review cycle → 'Assign KPI'. KPI=SALES_TGT (target pre-fills 50000), pick an employee, Weight=60. Assign. | The assignment row appears: status ASSIGNED, target 50000, no actual/rating yet.
KPI-04 | KPI measure — linear (M390) | HR Admin | On the SALES_TGT assignment click 'Measure'. Actual value=50000, Period=2026-Q2. Record. | Achievement = 100%, Rating = 5.00 (linear: achievement ÷ 20). Status becomes MEASURED.
KPI-05 | KPI measure — linear partial (M390) | HR Admin | Measure the same assignment again with Actual=30000 (Period=2026-Q3). | Achievement = 60%, Rating = 3.00. Click 'History' — BOTH measurements are listed (Q2 100%/5.00 and Q3 60%/3.00) with who/when.
KPI-06 | KPI measure — threshold (M390) | HR Admin | Assign CSAT (target 90) to an employee, then Measure with Actual=90. | Achievement = 100%, Rating = 4.00 (threshold bands: ≥110→5, ≥100→4, ≥80→3, ≥60→2, else 1 — hitting target = 4; beating it by 10% = 5).
KPI-07 | KPI duplicate guard (M390) | HR Admin | Try to assign SALES_TGT to the SAME employee in the SAME cycle again. | Rejected — the KPI is already assigned to that employee for this cycle.
KPI-08 | KPI cancel (M390) | HR Admin | Assign any KPI to another employee, then click Cancel on that row and confirm. | Status becomes CANCELLED; Measure is no longer offered on that row.
OKR-01 | OKR objectives (M391) | HR Admin | Performance → OKRs → 'New objective'. Title='Increase market share', Level=Company, pick a cycle, Confidence=High. Save. | The company objective appears with the Company level tag, 0% progress and HIGH confidence.
OKR-02 | OKR alignment (M391) | HR Admin | Create a second objective: Title='Grow enterprise sales', Level=Department, 'Aligns to' = Increase market share. Save. | The department objective appears showing '↑ Increase market share' under its title (parent alignment §8.3).
OKR-03 | OKR individual owner (M391) | HR Admin | Create a third objective with Level=Individual but leave Owner empty. Save. | Rejected — an Individual objective requires an owner employee. Pick an owner and save again — it appears with the owner's name.
OKR-04 | Key results (M391) | HR Admin | On 'Grow enterprise sales' click '+ KR'. Title='Sign 10 enterprise deals', Measurement=Number, Baseline=0, Target=10, Weight=60. Save. Add a second KR: 'Raise win rate to 40%', Percent, Baseline=20, Target=40, Weight=40. | Expanding the objective row shows both KRs at 0% progress with their weights.
OKR-05 | Check-in + roll-up (M391) | HR Admin | On the objective click 'Check-in'. Key result='Sign 10 enterprise deals', New current value=5, Confidence=Medium, Comment='Half way'. Record. | The KR goes to 50% progress; the OBJECTIVE progress becomes 30% (weighted: 50%×60 + 0%×40 = 30). The success message shows the new progress.
OKR-06 | Second check-in (M391) | HR Admin | Check-in again: KR='Raise win rate to 40%', New current value=30. | That KR shows 50% ((30−20)/(40−20)); objective progress becomes 50% (50×60 + 50×40 = 50). Click History — both check-ins are listed with old → new values, confidence and comments.
OKR-07 | Objective-level comment (M391) | HR Admin | Check-in with NO key result selected — just Confidence=Low and a comment 'Market headwinds'. Record. | The check-in is recorded in History as a comment; the objective's confidence tag changes to LOW; progress is unchanged.
OKR-08 | Close / reopen (M391) | HR Admin | On the objective click Close and confirm. Then try Check-in / Edit. | Status becomes CLOSED; Check-in / + KR / Edit disappear. Reopen restores it to ACTIVE.
SEC-A1 | Permissions (Phase A) | HR Specialist | Sign in as HR Specialist (hrspec). Open Performance → Rating scales and Review templates. | The lists are visible but 'New scale…' / 'New template…' / Edit are unavailable (write is HR Admin only).
SEC-A2 | Permissions (Phase A) | Employee | Sign in as a plain Employee. Try opening /performance/kpis and /performance/okrs directly. | The employee cannot see other employees' KPI assignments or OKR admin data (read is HR + managers; the API returns no rows / access denied for out-of-scope employees).
SEC-A3 | Permissions (Phase A) | Manager | Sign in as a Manager (manager). Open Performance → KPIs → Assignments. | The manager can view and assign/measure KPIs (managers are allowed to manage their team's KPIs); employee lists respect the manager's hierarchy scope.

## Sign-off
Performance UAT — Sign-off
Feature Area | Result | Tester | Date
Rating scales (SCL)
Review templates + cycle scoping (TPL)
KPI library + assignments + scoring (KPI)
OKR objectives + key results + check-ins (OKR)
Permissions (SEC)
Overall decision (SHIP / DON'T SHIP):
Tester name:
Date: