## Instructions
Compensation Management — User Acceptance Test (UAT) Script
HCM_10 Compensation Management • front-end (browser) testing • grows as each phase ships
How to use | Open the 'Test Cases' sheet. Do exactly what the Steps say (which menu, which button, what to type), compare to the Expected Result, and pick Pass / Fail / Blocked / Not Run in the Result column. Add anything unusual under Tester Notes. Fill the Sign-off sheet at the end.
Application URL | http://localhost:5180 — sign in first. Compensation features are under the top-nav 'Compensation' menu.
Delivered so far | Phase A — Pay Bands, Compensation Settings, Change Reasons, and the Employee Compensation Profile (compa-ratio + range penetration + salary history). Later phases (salary-change approvals, merit cycles, budgets, incentives/commission, market data, total-comp statement) will be appended to this same file.
Logins you will need | HR Admin (full compensation access), HR Specialist (read-only), Department Manager (own team only), Employee (self-service). If you only have an admin login, mark the role-restriction rows Blocked with a note.
Result values | Pass = worked as expected. Fail = did not match (add a note). Blocked = could not run (missing login/data). Not Run = skipped.
The two key numbers | Compa-ratio = salary ÷ band midpoint × 100. Range penetration = (salary − min) ÷ (max − min) × 100. If the employee's salary equals the band midpoint, compa-ratio is 100% and range penetration is 50%.

## Test Cases
Test ID | Feature Area | Login As | Test Steps (what to click / type) | Expected Result | Result | Tester Notes
SET-01 | Setup | HR Admin | Sign in as HR Admin. Make sure at least one salary grade exists with a Min and Max salary (Staffing/Grades), and a test employee 'Test One' who has a current salary and is linked to that grade (via their position). | The grade shows Min/Max; the employee has a salary and a grade.
CFG-01 | Settings (M359) | HR Admin | Top menu Compensation → Settings. Set 'Max increase % without approval' = 15, 'Budget exceeded policy' = WARNING, 'Default currency' = AZN. Save. | Saved with a green confirmation; reopening the page shows the saved values.
PB-01 | Pay Bands (M359) | HR Admin | Compensation → Pay Bands → Create. Code=IT-B3, Name=IT Band 3, Grade=(the test grade), Currency=AZN, Min=1500, Mid=2500, Max=3500, Effective From=today. Save. | New row IT-B3 appears with Min 1500 / Mid 2500 / Max 3500 and an Active tag.
PB-02 | Pay Bands (M359) | HR Admin | Create a band with Min=3000, Mid=2000, Max=3500 (min greater than mid). Save. | Rejected — the band range is invalid (min must be ≤ mid ≤ max); an error message is shown, the row is not created.
PB-03 | Pay Bands (M359) | HR Admin | Create another band re-using the code IT-B3. Save. | Rejected — band code must be unique; error shown.
PB-04 | Pay Bands (M359) | HR Admin | On the IT-B3 row click Deactivate and confirm. | The band shows as Inactive (not physically deleted); it no longer counts as an active band.
CR-01 | Change Reasons (M359) | HR Admin | Compensation → Change Reasons. | Six seeded reasons are present: Annual Merit, Promotion, Market Adjustment, Retention, Equity Adjustment, Correction — each with a category tag.
CR-02 | Change Reasons (M359) | HR Admin | Create a new reason (Code=SPECIAL_ADJ, Name=Special Adjustment, Category=ADJUSTMENT). Save. Then Deactivate it. | The new reason appears, then shows Inactive after deactivation.
CP-01 | Compensation Profile (M360) | HR Admin | Compensation → Compensation Profile. In the employee selector search and pick the test employee. | A header card shows the employee name, grade, band and current salary with currency + effective date.
CP-02 | Compensation Profile (M360) | HR Admin | On the profile, read the Compa-ratio card. (Compa-ratio = salary ÷ band midpoint × 100.) Example: salary 2500 and midpoint 2500 → 100%. | The Compa-ratio value is correct for the employee's salary vs the band midpoint (100% when salary equals midpoint).
CP-03 | Compensation Profile (M360) | HR Admin | Read the Range penetration card. (= (salary − min) ÷ (max − min) × 100.) Example: salary 2500, min 1500, max 3500 → 50%. | The Range-penetration value is correct (50% when the salary sits at the midpoint of the band).
CP-04 | Compensation Profile (M360) | HR Admin | Look at the range-position tag next to the figures. | The tag colour matches the position: green for MID, gold for LOW/HIGH, red for BELOW_MIN/ABOVE_MAX.
CP-05 | Compensation Profile (M360) | HR Admin | Scroll to the Salary history table. | Past salary records are listed (salary, effective from/to, reason), most recent first — none are missing or overwritten.
CP-06 | Compensation Profile (M360) | Department Manager | Sign in as a Department Manager. Open Compensation → Compensation Profile and try to view an employee who is NOT in your team. | Access is denied for employees outside your hierarchy (an error/permission message); your own team members are viewable.
SEC-01 | Permissions (Phase A) | HR Specialist | Sign in as HR Specialist. Open the Compensation menu. | Can view the Compensation Profile / Pay Bands / Change Reasons, but the create/edit/Save actions and Settings are not available (read-only).
SEC-02 | Permissions (Phase A) | Employee | Sign in as a plain Employee. | The Compensation admin menu (Pay Bands, Change Reasons, Settings) is not available.

## Sign-off
Compensation UAT — Sign-off
Feature Area | Result | Tester | Date
Settings (CFG)
Pay Bands (PB)
Change Reasons (CR)
Compensation Profile (CP)
Permissions (SEC)
Phase A decision (SHIP / DON'T SHIP):
Tester name:
Date: