## Instructions
Benefits Administration — User Acceptance Test (UAT) Script
HCM_11 Benefits Administration • front-end (browser) testing • grows as each phase ships
How to use | Open the 'Test Cases' sheet. Do exactly what the Steps say (which tab, which button, what to type), compare to the Expected Result, and pick Pass / Fail / Blocked / Not Run in the Result column. Add anything unusual under Tester Notes. Fill the Sign-off sheet at the end.
Application URL | http://localhost:5180 — sign in first. Benefits features are under the top-nav 'Benefits' page.
Delivered so far | Phases A–F COMPLETE (the whole module). A: Categories (M373), Providers (M374), Plans + coverage tiers + eligibility rules (M375). B: enrolment with tiers + dependant-level coverage (M376), enrolment approval workflow (M377), payroll deduction bridge — pre-tax recurring deductions (M378). C: open-enrolment windows (M379), qualifying life events (M380). D: benefit claims + approval/payout (M381/M382). E: Total-Comp employer-benefits + cost report (M383), provider-file reconciliation (M384). F: employee self-service Benefits tab (M385), benefits dashboard (M386), notifications (M387).
Logins you will need | HR Admin (full benefits access), HR Specialist (read-only), Payroll Specialist (payroll runs), Employee (self-service). If you only have an admin login, mark the role-restriction rows Blocked with a note.
Result values | Pass = worked as expected. Fail = did not match (add a note). Blocked = could not run (missing login/data). Not Run = skipped.
Good to know | Categories drive tax treatment + whether a plan needs a provider. Plans link to a category, a plan year and a provider from the master. Coverage tiers set the employer/employee split per coverage level; eligibility rules decide who may enrol (enforced from Phase B).

## Test Cases
Test ID | Feature Area | Login As | Test Steps (what to click / type) | Expected Result | Result | Tester Notes
SET-01 | Setup | HR Admin | Sign in as HR Admin at http://localhost:5180. Open the top-nav 'Benefits' page (Benefits administration). You should see tabs: Categories, Providers, Plans catalog, Enrolments, My benefits. | The Benefits page opens with the five tabs visible.
CAT-01 | Categories (M373) | HR Admin | Benefits → Categories tab. | Eight seeded categories are listed in order: Health Insurance, Life Insurance, Pension / Retirement, Meal Allowance, Transport Allowance, Housing Allowance, Mobile / Communication, Wellness Program.
CAT-02 | Categories (M373) | HR Admin | On the Categories list, read the Taxable and Provider columns for Health vs Meal. | Health = Exempt + Provider Required; Meal = Taxable + no provider. (Insured plans are tax-exempt; cash-like allowances are taxable.)
CAT-03 | Categories (M373) | HR Admin | Click 'New category…'. Code=GYM, Name=Gym Membership, tick Taxable off, Provider off, Order=9. Save. | The new category GYM appears at the end of the list, Active.
CAT-04 | Categories (M373) | HR Admin | Click 'New category…' again and re-use the code HEALTH. Save. | Rejected — category code must be unique; an error is shown and no row is created.
CAT-05 | Categories (M373) | HR Admin | Open the GYM category, untick Active, Save. Then toggle the 'Active only' switch. | GYM shows Inactive (not deleted); with 'Active only' on it is hidden from the list.
PRV-01 | Providers (M374) | HR Admin | Benefits → Providers tab → 'New provider…'. Code=PASHA-INS, Name=Pasha Insurance OJSC, Type=Insurer, Contact email=account@pasha.az, Contract number=C-2026-01, Contract window = today → +1 year. Save. | The provider PASHA-INS appears in the table with type Insurer, the contract number and the contract window.
PRV-02 | Providers (M374) | HR Admin | Create a provider with a Contract window whose end date is BEFORE its start date. Save. | Rejected — contract end must be on/after start; an error is shown.
PRV-03 | Providers (M374) | HR Admin | Create a second provider (Code=CAPITAL-PF, Name=Kapital Pension Fund, Type=Pension fund). Save. | The pension-fund provider appears.
PRV-04 | Providers (M374) | HR Admin | Enter an invalid email (e.g. 'abc') in Contact email and try to save. | Rejected — the email format is validated.
PLN-01 | Plans (M375) | HR Admin | Benefits → Plans catalog → 'New plan…'. Code=HEALTH-FAM-26, Name=Family Health 2026, Type=Health, Category=HEALTH — Health Insurance, Plan year=2026, Provider (from master)=Pasha Insurance, Employer/mo=120, Employee/mo=30, Effective window=this year. Save. | The plan appears in the table showing the Category tag (Health Insurance), Year 2026 and Provider = Pasha Insurance OJSC (the master name, not free text).
PLN-02 | Plans (M375) | HR Admin | On the HEALTH-FAM-26 row click 'Tiers…'. In the Coverage tiers section click 'Add tier' three times and set: Employee only Er=100/Ee=0; Employee + spouse Er=150/Ee=40; Family Er=220/Ee=90 (add a Cover/sum-insured on one). Save. | The three tiers save; reopening 'Tiers…' shows them with the right employer/employee amounts.
PLN-03 | Plans (M375) | HR Admin | Reopen 'Tiers…' and add a second tier with the SAME tier code as an existing one (e.g. two 'Family'). Save. | Rejected — each coverage tier code must be unique (message shown).
PLN-04 | Plans (M375) | HR Admin | In 'Tiers…' → Eligibility rules, click 'Add rule'. Employment type=FULL_TIME, Min service=3 (mo), Note='FT after probation'. Save. | The eligibility rule saves; reopening shows it. (No rules = open to all; this rule limits the plan to full-time staff with 3+ months service — enforced at enrolment in Phase B.)
PLN-05 | Plans (M375) | HR Admin | Open the plan editor for HEALTH-FAM-26 and confirm Category and Plan year are populated; change Provider (from master) to blank and instead type a free-text Provider. Save, then look at the Provider column. | With a master provider it shows the master name; cleared, it falls back to the free-text provider name.
SEC-A1 | Permissions (Phase A) | HR Specialist | Sign in as HR Specialist. Open Benefits → Categories / Providers / Plans. | You can view the lists, but 'New…' / Save / the Tiers… editor are read-only or unavailable (write is HR Admin / Benefits Manager only).
SEC-A2 | Permissions (Phase A) | Employee | Sign in as a plain Employee and open the Benefits page. | Only the 'My benefits' tab is available — the admin tabs (Categories, Providers, Plans, Enrolments) are hidden.
SETB | Setup B | HR Admin | Pick a test employee who has at least one benefit-eligible dependant (Employee profile → Dependants → make sure 'Benefit eligible' or 'Insurance eligible' is ticked on one). Copy the employee's UUID from their profile URL. Make sure the HEALTH-FAM-26 plan from Phase A has coverage tiers (Tiers… editor). | The employee has an eligible dependant and you have their UUID; the plan has tiers.
ENR-01 | Enrolments (M376) | HR Admin | Benefits → Enrolments → 'Enrol employee…'. Pick the plan; paste the employee UUID (eligible dependants load below); pick a Coverage tier (e.g. Employee + spouse); tick a dependant; Start date today; Status = Enrolled. Enrol. | A new ENROLLED row appears showing the Tier tag, the covered-dependant count (hover shows the name) and the Employee/mo amount taken from the chosen tier (not the plan flat rate).
ENR-02 | Enrolments (M376) | HR Admin | Enrol the same or another employee with NO tier selected. | The enrolment uses the plan's flat employer/employee contribution; Tier column shows 'flat'.
ENR-03 | Enrolments (M376) | HR Admin | Try to enrol and tick a dependant who is NOT benefit/insurance eligible (or belongs to a different employee). | Rejected — only eligible dependants of that employee can be covered (error shown). Ineligible dependants don't even appear in the list.
APR-01 | Approvals (M377) | HR Admin | Enrol an employee but set Status = 'Draft (submit for approval)'. Then on that DRAFT row click Submit. | Status goes DRAFT → PENDING_APPROVAL and the request appears in the Approvals inbox.
APR-02 | Approvals (M377) | HR Admin | Open the Approvals inbox and approve the pending benefit enrolment. | After approval the enrolment status becomes ENROLLED (coverage now active).
APR-03 | Approvals (M377) | HR Admin | Submit another draft enrolment, then reject it in the Approvals inbox. | The enrolment status becomes REJECTED (coverage never activates).
APR-04 | Approvals (M377) | HR Admin | On a DRAFT (not yet submitted) or PENDING enrolment click Cancel. | Status becomes CANCELLED; nothing activates.
SUS-01 | Suspend/Resume (M376) | HR Admin | On an ENROLLED row click Suspend and confirm; then click Resume. | Status toggles ENROLLED → SUSPENDED → ENROLLED. (Suspending pauses the payroll deduction; resuming restarts it — see DED-03.)
DED-01 | Payroll bridge (M378) | HR Admin | Enrol an employee (Status Enrolled) in a plan whose Employee/mo contribution is > 0 (e.g. 30). Then open Payroll → Deductions for that employee (or the employee's payslip preview). | A RECURRING payroll deduction 'Benefit contribution: <plan>' for the employee amount (e.g. 30.00) is present and ACTIVE, starting the enrolment month.
DED-02 | Payroll bridge (M378) | HR Admin | Enrol an employee in an employer-paid plan (Employee/mo = 0). | NO payroll deduction is created (nothing to deduct).
DED-03 | Payroll bridge (M378) | HR Admin | Terminate (or Suspend) the DED-01 enrolment, then re-check that employee's deductions. | The benefit-contribution deduction is now CANCELLED (not deleted). Re-running payroll for a later month no longer deducts it.
DED-04 | Payroll bridge (M378) | Payroll Specialist | Run payroll for a period where the DED-01 employee is enrolled; open their payslip. | Net pay is reduced by the benefit employee-contribution (pre-tax: it lowers taxable gross before tax/DSMF/MMI). The deduction shows in the payslip breakdown.
SEC-B1 | Permissions (Phase B) | HR Specialist | Sign in as HR Specialist and open Benefits → Enrolments. | You can view enrolments but cannot enrol / submit / approve / suspend / terminate (write is HR Admin / Benefits Manager only).
OE-01 | Open enrollment (M379) | HR Admin | Benefits → Open enrollment → 'New window…'. Plan year=2026, Name='2026 Annual OE', window = a range that INCLUDES today. Save. | The window appears; its 'Open now' column shows OPEN (because today is inside the range).
OE-02 | Open enrollment (M379) | HR Admin | Create another window whose date range is entirely in the past (or future). Save. | 'Open now' shows closed for that window.
OE-03 | Open enrollment (M379) | HR Admin | Create a window with end date BEFORE start date. Save. | Rejected — end must be on/after start (error shown).
LE-01 | Life events (M380) | HR Admin | Benefits → Life events → 'Report life event…'. Paste an employee UUID, Event type=Marriage, Event date=today, Window days=30. Report. | A PENDING life event appears for that employee; the special-window column shows closed (not yet approved).
LE-02 | Life events (M380) | HR Admin | On the PENDING life event click Approve. | Status becomes APPROVED and 'Special window' shows OPEN (event date + 30 days covers today).
LE-03 | Life events (M380) | HR Admin | Report another event and click Reject. | Status becomes REJECTED; no special window opens.
CL-01 | Claims (M381) | HR Admin | Benefits → Claims → 'New claim…'. Paste an employee UUID, Claim date=today, add 2 line items with descriptions + amounts (e.g. 40 and 60). Create draft. | A DRAFT claim BC-#### appears with Total = 100. Expand the row to see the two line items.
CL-02 | Claims (M382) | HR Admin | On the DRAFT claim click Submit, then Approve. | Status goes DRAFT → SUBMITTED → APPROVED (approved amount = total unless changed).
CL-03 | Claims (M382) | HR Admin | On the APPROVED claim click 'Mark paid'. | Status becomes PAID; a payment reference is recorded (expand row to see it). Note: payment is tracking-only — it is NOT pushed to payroll.
CL-04 | Claims (M382) | HR Admin | Create another claim, Submit it, then Reject it. | Status becomes REJECTED.
CL-05 | Claims (M382) | Employee | Sign in as the claim's employee → My Workspace → Benefits tab → My claims. | The employee sees their own claims and statuses (and only their own).
CST-01 | Total-Comp benefits (M383) | HR Admin | Make sure the employee has an ACTIVE enrolment with an employer contribution (e.g. 100/mo). Then Compensation → Total Comp Statements → Generate for that employee's year → open/download. | The statement's 'Employer benefits' line is NON-ZERO (≈ employer monthly × active months), and the Total includes it. (Previously this was always 0.)
REC-01 | Reconciliation (M384) | HR Admin | Benefits → Providers → 'Reconcile file…'. Pick a provider that has plans with active enrolments. In the paste box enter lines 'employeeNo,amount' — include one matching member with the correct total, one with a WRONG amount, and one employeeNo that is NOT enrolled. Reconcile. | The report shows: MATCHED for the correct one, AMOUNT MISMATCH for the wrong amount, EXTRA IN FILE for the non-enrolled one, and MISSING IN FILE for any enrolled member you left out. Counts + system/file totals are shown.
DSH-01 | Dashboard (M386) | HR Admin | Benefits → Dashboard. | Stat cards populate: active enrolments, active/total plans, pending approvals, expiring plans (60d), employer & employee monthly spend, employer annual, open life-event windows — with sensible numbers.
DSH-02 | Dashboard (M386) | HR Admin | Look at 'Employer spend by category' and the 'Enrolments by status' / 'Claims' cards. | The category table sums employer/employee monthly per category; status tags show the enrolment + claim counts; total paid claims is shown.
SS-01 | Self-service (M385) | Employee | Sign in as an enrolled Employee → My Workspace → Benefits tab. | Shows active plans, your monthly contribution, employer contribution, each plan (tier, dependants covered) and your claims — only your own data.
NT-01 | Notifications (M387) | HR Admin / Employee | Activate an enrolment (direct enrol or approve a submitted one) for an employee who has a user login; then approve/reject one of their claims. Sign in as that employee and check the notifications bell. | The employee receives in-app notifications: 'coverage active' on enrolment activation, and claim approved/rejected on the claim decision.
SEC-CF | Permissions (Phase C–F) | HR Specialist | As HR Specialist, open Open enrollment / Life events / Claims / Reconcile / Dashboard. | Read surfaces are visible per role; create/approve/reject/reconcile write actions are unavailable (write = HR Admin / Benefits Manager).

## Sign-off
Benefits UAT — Sign-off
Feature Area | Result | Tester | Date
Categories (CAT)
Providers (PRV)
Plans + Tiers + Eligibility (PLN)
Enrolment: tiers + dependants (ENR)
Enrolment approval (APR)
Suspend / Resume (SUS)
Payroll deduction bridge (DED)
Open enrollment (OE)
Life events (LE)
Claims (CL)
Total-Comp + reconciliation (CST/REC)
Dashboard + self-service (DSH/SS)
Notifications (NT)
Permissions (SEC)
Overall decision (SHIP / DON'T SHIP):
Tester name:
Date: