## Instructions
Goals / LMS / Talent / Succession / Career (HCM_13-17) — UAT Script
HCM_13-17 bundle • front-end (browser) testing • grows as each phase ships
How to use | Open the 'Test Cases' sheet. Do exactly what the Steps say (which tab, which button, what to type), compare to the Expected Result, and pick Pass / Fail / Blocked / Not Run in the Result column. Add anything unusual under Tester Notes. Fill the Sign-off sheet at the end.
Application URL | http://localhost:5180 — sign in first. Features live under the Performance, Learning and Talent top-nav menus.
Delivered so far | ALL PHASES COMPLETE. HCM_13: goal-type catalog wired into goals (M403). HCM_14: instructors + rooms (M404), classroom sessions + capacity + attendance (M405), mandatory-training rules + auto-enrol sweep + compliance (M406), training costs (M407), post-training feedback + instructor rating (M408). HCM_15: talent profile HiPo/retention (M409), talent pools (M410), talent review cycles/9-box → profile roll-up (M411), talent analytics (M412). HCM_16: critical positions + succession plans + approval workflow (M413), risk/impact-of-loss (M414), replacement chart + coverage + dev-plan bridge (M415). HCM_17: career paths (M416), mentoring (M417), career dashboard + internal job recommendations (M418).
Logins you will need | HR Admin (full admin), HR Specialist (read-only talent checks), Manager (hierarchy checks), Employee (self-service + confidentiality checks). If you only have an admin login, mark role-restriction rows Blocked with a note.
Result values | Pass = worked as expected. Fail = did not match (add a note). Blocked = could not run (missing login/data). Not Run = skipped.
CONFIDENTIALITY rule under test | Employees must NEVER see their own (or anyone's) HiPo flag, retention risk, talent review or succession nomination — these are HR/executive-only. Several SEC cases verify exactly this; treat any leak as an automatic Fail + report immediately.

## Test Cases
Test ID | Feature Area | Login As | Test Steps (what to click / type) | Expected Result | Result | Tester Notes
SET-01 | Setup | HR Admin | Sign in as HR Admin at http://localhost:5180. Check the top nav: Performance menu (Goals), Learning menu (Classroom training, Mandatory training) and the new Talent menu (Pools, Reviews, Analytics, Succession plans, Replacement chart, Career paths, Mentoring, Career dashboard). | All the listed menu entries are present.
GT-01 | Goal types (M403) | HR Admin | Performance → Goals → open the 'New goal' form and expand the Goal type dropdown. | 14 seeded goal types are offered (Revenue, Sales, Cost optimisation, Project delivery, Quality, Customer satisfaction, Operational excellence, Compliance, Safety, Innovation, Leadership, Team development, Personal development, Process improvement).
GT-02 | Goal types (M403) | HR Admin | Create a goal picking Type='Personal development'. Watch the Category field as you pick the type. Save and find the goal in the list. | Picking the type auto-selects its category (DEVELOPMENT); the saved goal's row shows the type as a tag in the Type column.
INS-01 | Instructors (M404) | HR Admin | Learning → Classroom training → Instructors tab → 'New instructor'. Pick an internal employee, specialization 'Leadership', hourly cost 50. Save. Then create a SECOND instructor with NO employee but External name 'ACME Training Ltd'. | Both instructors appear — one shows the employee's name (internal), the other the external name. An instructor with neither employee nor external name is rejected.
ROM-01 | Rooms (M404) | HR Admin | Rooms tab → 'New room'. Code=TR-1, Name='Training room 1', Capacity=2. Save. Create a second room marked Virtual. | Both rooms appear; the virtual one carries a Virtual tag.
SES-01 | Sessions (M405) | HR Admin | Sessions tab → 'New session'. Pick a published course, instructor, room TR-1 (capacity 2), today 10:00→12:00. Save. | The session appears as SCHEDULED with course/instructor/room columns filled. An end time before the start time is rejected.
SES-02 | Capacity (M405) | HR Admin | Open the session's attendance drawer and enrol 2 employees. Then try enrolling a 3rd. | First two enrol OK (ENROLLED). The 3rd is rejected — room TR-1 capacity (2) is full. Enrolling the SAME employee twice is also rejected.
SES-03 | Attendance marking (M405) | HR Admin | Mark one enrolled employee ATTENDED and leave the other ENROLLED. Then set the session status to COMPLETED. | The ATTENDED row gets a check-in timestamp; on COMPLETED the still-ENROLLED employee is auto-finalised to NO_SHOW.
SES-04 | Edit guard (M405) | HR Admin | Try editing the now-COMPLETED session (change its time). | Rejected — only SCHEDULED sessions can be edited.
MND-01 | Mandatory rule (M406) | HR Admin | Learning → Mandatory training → 'New rule'. Pick a published course, audience = one department, recurrence 12 months, due days 30. Save. | The rule appears, Active, with the audience and recurrence shown.
MND-02 | Sweep (M406) | HR Admin | Click 'Run sweep now'. Then check Learning → My learning (or the course's enrolments) for an employee in that department. | The sweep reports how many were enrolled; in-scope ACTIVE employees now have an ASSIGNED enrolment with a due date ~30 days out. Running the sweep again enrols 0 (idempotent).
MND-03 | Compliance (M406) | HR Admin | Open the rule's compliance view. | Per-rule counts show in-scope / compliant / pending / overdue that match the enrolments just created.
CST-01 | Training costs (M407) | HR Admin | On the classroom page open the costs surface for the completed session (or course). Add cost lines: INSTRUCTOR 100 AZN and CATERING 40 AZN. | Both lines save and list with a total; a negative amount is rejected.
FBK-01 | Feedback (M408) | HR Admin | Submit training feedback for the session as the ATTENDED employee (ratings 1–5: content 5, instructor 4, overall 5; anonymous ON). Then try submitting feedback for the NO_SHOW employee. | The attendee's feedback saves (one per employee per session). The non-attendee is rejected — feedback requires attendance.
FBK-02 | Anonymous + instructor rating (M408) | HR Admin | View the session's feedback as HR and check the instructor's row on the Instructors tab. | The anonymous feedback shows NO employee identity; the instructor's average rating updated from the submitted instructor score.
TPR-01 | Talent profile (M409) | HR Admin | Talent → (profiles surface) → upsert a profile for employee A: HiPo ON (Manual), Retention risk HIGH, risk reason, retention action, mobility INTERNAL, aspirations. | The profile saves and lists employee A with HiPo + HIGH risk tags. Filtering by HiPo-only / risk works.
TPR-02 | Career interests (M409) | Employee | Sign in as an employee. Via My Workspace / career dashboard, add a career interest: target role 'Team Lead', timeline 1–2 years. Then delete it and re-add. | The interest saves, lists and deletes — employees manage their OWN interests. A blank target role is rejected.
SEC-15A | CONFIDENTIALITY (M409) | Employee | As employee A (who has the HiPo/HIGH-risk profile), call GET /api/talent/profiles and /api/talent/profiles/employees/<own id> (or try the Talent pages). | Access denied — employees NEVER see talent profiles, including their own HiPo flag and retention risk. Talent pages/menu are hidden for plain employees.
POOL-01 | Talent pools (M410) | HR Admin | Talent → Pools → 'New pool'. Code=LEAD_PIPE, Name='Leadership pipeline', purpose, review every 6 months. Save. Add 2 employees as members. Remove 1. | The pool saves; members add and list with who/when added; duplicate member add is rejected; removal works.
TRV-01 | Talent review (M411) | HR Admin | Talent → Reviews → create cycle 'Talent review 2026'. Record a review for employee B: performance box 3, potential box 3, HiPo decision YES, retention risk MEDIUM, notes. Save. | The review saves (9/9 box). Recording AGAIN for the same employee in the same cycle UPDATES the existing review (upsert, no duplicate row).
TRV-02 | Profile roll-up (M411) | HR Admin | After TRV-01, open employee B's talent profile. | The profile now shows HiPo=YES with source NINE_BOX and retention risk MEDIUM — the review decision rolled onto the profile automatically.
TAN-01 | Talent analytics (M412) | HR Admin | Talent → Analytics → pick the 2026 cycle. | The 9-box distribution reflects the recorded reviews; HiPo count/% matches; the retention-risk breakdown and pool coverage (pools + member counts) populate.
SUC-01 | Critical positions (M413) | HR Admin | Talent → Succession plans → Critical positions tab → mark a position critical: reason, replacement difficulty HIGH, vacancy risk CRITICAL, succession required. | The critical position is listed with its difficulty/risk tags.
SUC-02 | Succession plan + approval (M413) | HR Admin | Plans tab → 'New plan' for that critical position: plan owner, effective/review dates, emergency successor. Save (DRAFT), then Submit for approval. Approve it from the Approvals inbox (HR). | DRAFT → SUBMITTED starts a SUCCESSION_PLAN_APPROVAL workflow; approving flips the plan to APPROVED; rejecting another plan returns it to DRAFT. Both transitions are audit-logged.
RSK-01 | Risk of loss (M414) | HR Admin | Open the succession nominations page (9-box/succession area) and edit a nomination: Risk of loss HIGH, Impact of loss CRITICAL, risk reason, retention action. | The nomination saves and its row shows the risk/impact tags; invalid values outside LOW/MEDIUM/HIGH/CRITICAL are rejected.
CHT-01 | Replacement chart (M415) | HR Admin | Talent → Replacement chart. | Each critical position shows its incumbent(s) and nominated successors with readiness + risk; coverage cards count positions with 0 / 1 / 2+ READY_NOW successors.
CHT-02 | Dev-plan bridge (M415) | HR Admin | On a successor nomination, attach a development plan (create one under Performance → Development plans first if needed). | The nomination links to the dev plan; the link is visible on the chart/nomination row.
CPT-01 | Career paths (M416) | HR Admin | Talent → Career paths → 'New path'. Code=ENG_TRACK, Name='Engineering track', job family. Add 2 steps: step 1 from Junior → Senior (required skills, 2 years, courses); step 2 Senior → Lead. Save. Re-open and edit a step, save again. | The path saves with ordered steps; re-saving (full replace) does not error and keeps the edited steps. All signed-in users can VIEW paths; only HR can edit.
MNT-01 | Mentor + request (M417) | HR Admin | Talent → Mentoring → register a mentor (employee M, areas 'Leadership', max mentees 1). Then as (or on behalf of) employee E request mentoring with mentor M. | The mentor registers; the request appears as REQUESTED with a default 6-month term.
MNT-02 | Capacity + lifecycle (M417) | HR Admin | Approve the request (→ ACTIVE). Then have a SECOND mentee request mentor M and try to approve it too. Finally COMPLETE the first relationship. | The second approval is rejected — mentor M is at max capacity (1 active). Completing the first frees capacity; statuses flow REQUESTED→ACTIVE→COMPLETED (or CANCELLED).
SEC-17A | Mentoring visibility (M417) | Employee | As an employee who is neither the mentor, the mentee nor HR, try to read the mentoring relationship / its meeting notes. | Denied — mentoring relationships and notes are visible only to the mentor, the mentee and HR.
CDB-01 | Career dashboard (M418) | Employee | Sign in as an employee → Talent → Career dashboard (own record). | The dashboard shows the employee's own career interests, development plans and mentoring status. NO HiPo/retention/succession data appears anywhere on it.
CDB-02 | Job recommendations (M418) | Employee | With a career interest whose target role matches an OPEN internal job posting's title, reload the dashboard. | The matching posting appears under recommendations with a match score (role-title match scores higher than department-only match).
CDB-03 | Scope guard (M418) | Manager | As a manager, open the career dashboard for one of YOUR reports, then try an employee OUTSIDE your hierarchy (by employeeId in the URL/API). | Your report's dashboard loads; the out-of-hierarchy employee is denied (access scope guard).
SEC-B1 | Permissions | HR Specialist | Sign in as HR Specialist. Open Talent pools / reviews / analytics / succession / replacement chart. | Readable (HR Specialist may VIEW talent + succession data) but create/edit actions are unavailable (writes = HR Admin only).
SEC-B2 | Permissions | Manager | Sign in as a Manager (not HR). Try the Talent pages (pools, reviews, analytics, succession plans). | Denied / hidden — talent-review, HiPo and succession data are HR-and-executive-only; managers see them only via HR-run sessions, not directly.
SEC-B3 | Permissions | Employee | Sign in as a plain Employee. Try /talent/pools, /talent/reviews, /talent/succession-plans and the classroom/mandatory ADMIN pages directly by URL. | All denied or empty — no talent/succession/LMS-admin surface leaks to employees; only their own career dashboard and interests work.

## Sign-off
HCM_13-17 bundle UAT — Sign-off
Feature Area | Result | Tester | Date
Goal types (GT)
Instructors + rooms (INS/ROM)
Classroom sessions + attendance (SES)
Mandatory training (MND)
Training costs + feedback (CST/FBK)
Talent profile + interests (TPR)
Talent pools (POOL)
Talent reviews + roll-up (TRV)
Talent analytics (TAN)
Critical positions + succession plans (SUC)
Risk of loss (RSK)
Replacement chart + coverage (CHT)
Career paths (CPT)
Mentoring (MNT)
Career dashboard + recommendations (CDB)
Permissions + confidentiality (SEC)
Overall decision (SHIP / DON'T SHIP):
Tester name:
Date: